## Sheet1
Stroke Co-design Project Plan
| Year 1 | [12 empty] | Year 2
Key activities | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  | Jul |  |  |  |  | Aug |  |  |  |  | Sept |  |  |  | Oct |  |  |  | Nov |  |  |  |  | Dec |  |  |  | Jan |  |  |  | Feb
| 5th | 12th | 19th | 26th | 2nd | 9th | 16th | 23rd | 2nd | 9th | 16th | 23rd | 30th | 6th | 13th | 20th | 27th | 4th | 11th | 18th | 25th | 1st | 8th | 15th | 22nd | 29th | 6th | 13th | 20th | 27th | 3rd | 10th | 17th | 24th | 31st | 7th | 14th | 21st | 28th | 5th | 12th | 19th | 26th | 2nd | 9th | 16th | 23rd | 30th | 7th | 14th | 21st | 28th | 4th | 11th | 18th | 25th | 1st | 8th | 15th | 22nd | 29th
Project Steering Group meetings | bar: Jan 5th; Feb 2nd; Mar 2nd; Mar 30th; Apr 27th; Jun 22nd; Jul 27th; Aug 24th; Sept 28th
Observations | bar: Jan 12th to Feb 2nd
Staff interviews (approx 15) | bar: Jan 26th to Feb 9th; Feb 23rd to Mar 2nd
Identify and recruit patients (and carers) | bar: Feb 2nd to Mar 9th
Patient (and carer) interviews (approx 12) | bar: Mar 2nd to Apr 6th
Analysis of staff and patient interview and observation data | bar: Mar 30th to Apr 20th
Edit film | bar: Apr 20th to May 4th
Patients view and approve films | bar: May 18th to May 25th
Patient feedback event | bar: Jun 1st
Re-edit film and add introduction if required | bar: Jun 8th
Staff feedback event | bar: Jun 15th
Joint patient and staff event | bar: Jul 29th
Co-design groups implement improvements | bar: Jul 13th; Jul 27th; Aug 10th; Aug 24th; Sept 7th; Sept 21st; Oct 5th; Oct 19th; Nov 9th; Nov 30th
Collate outputs from co-design groups | bar: Nov 23rd to Jan 25th
Celebration event | bar: Feb 8th