## Sheet1
GHNHSFT PERFORMANCE IN DELIVERY Q1 2018 2019
| Id | Research Ethics Committee Reference Number | Integrated Research Application System Number | Name of Trial | Target Number Of Patients Agreed? | Minimum Number Of Patients Agreed | Maximum Number Of Patients Agreed | Target Date To Recruit Patients Agreed? | .Date Agreed to recruit target number of patients | Total Number Of Patients Recruited At The Agreed Target Date | Date That The Trial Closed To Recruitment | Total Number Of Study Participants Recruited | Reason For Closure Of Trial | COMMENTS
| 30789 | 16/EE/0243 | 207331 | A 6-MONTH, MULTICENTER, PHASE 3, OPEN-LABEL EXTENSION SAFETY STUDY OF OTO-104 GIVEN AT 3-MONTH INTERVALS BY INTRATYMPANIC INJECTION IN SUBJECTS WITH UNILATERAL MENIERE’S DISEASE | Number Agreed | 5 | 5 | Date Agreed | 2017-05-31 | 11 | 2017-09-05 | 11 | Recruitment Finished | PROJECT RECRUITED BEYOND SET TARGET, TO TIME AND NO ISSUES
| 30790 | 15/LO/1812 | 190810 | riva cassini - Efficacy and Safety of Rivaroxaban Prophylaxis Compared with Placebo in Ambulatory Cancer Patients Initiating Systemic Cancer Therapy and at High Risk for Venous Thromboembolism | Number Agreed | 5 | 5 | Date Agreed | 2017-11-23 | 9 | 2017-11-23 | 9 | Recruitment Finished | PROJECT RECRUITED BEYOND SET TARGET