## Sheet1
GHNHSFT PERFORMANCE IN INITIATING QUARTER 3 OF 2018/2019
id | Research Ethics Committee Reference Number | Integrated Research Application System Number | Name of Trial | First Participant Recruited? | Date of First Participant Recruited | Duration between Date Site Selected and Date Site Confirmed | Duration between Date Site Confirmed and First Participant Recruited | Duration between Date Site Selected and First Participant Recruited | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Date Site Ready To Start | Reasons for Delay | Comments | Reasons for delay correspond to:
133810 | 16/WS/0165 | 190574 | ADSCAN - A Randomised Phase II study of Accelerated, Dose escalated, Sequential Chemo-radiotherapy in Non-small Cell Lung Cancer. | No |  | 6 |  |  | 2018-01-04 | 2018-01-04 | 2016-11-08 | 2018-02-09 | 2018-01-10 | 2018-02-28 | I - Rare diseases | ADSCAN HAS AN ANNUAL RECRUITMENT TARGET OF 2.5, THE OVERALL SITE RECRUITMENT TARGET IS 5-6. RARE DISEASES CATEGORISATION. | Neither
133811 | 15/NS/0113 | 188563 | XRS PURE - The clinical and cost effectiveness of surgical interventions for stones in the lower kidney: The PUrE RCTPercutaneous Nephrolithotomy (PNL), Flexible Ureterorenoscopy (FURS) and Extracorporeal Lithotripsy (ESWL) for lower pole Kidney stones | Yes | 2018-11-29 | 102 | 213 | 315 | 2018-01-18 | 2018-01-18 | 2015-11-12 | 2018-04-23 | 2018-04-30 | 2018-05-01 | E - Staff availability issues | THE SET UP FOR XRS PURE, WAS INITIALLY DELAYED DUE TO GHNHSFT NOT HAVING THE STAFF CAPACITY TO SUPPORT THE TRIAL. THE PROJECT WAS REVIEWED AS FEASIBLE UPON THE APPOINTMENT OF STAFF. SINCE THIS TIME, WE HAVE ALSO EXPERIENCED A DELAY IN HOSTING AN INITIATION VISIT DUE TO A REARRANGED MEETING AS A RESULT OF PREVIOUSLY CANCELLED MEETING DUE TO EXTREME WEATHER CONDITIONS. STAFF ARE IN PLACE, SIV HAS TAKEN PLACE THE PROJECT IS APPROVED TOMORROW ON 01/05/18 | NHS Provider
133812 | 17/NE/0149 | 190810 | RIVA CASSINI - A Randomized, Double-Blind, Placebo-Controlled Phase 3 Study of Rovalpituzumab Tesirine as Maintenance Therapy Following First-Line Platinum-Based Chemotherapy in Subjects with Extensive Stage Small Cell Lung Cancer (MERU) | Yes | 2018-07-25 | 14 | 174 | 188 | 2017-10-05 | 2018-01-18 | 2017-06-01 | 2018-01-23 | 2018-02-01 | 2016-06-02 | I - Rare diseases |  | Neither
133813 | 15/LO/1904 | 173980 | MROC - The Impact of Multiparametric MRI on the Staging and Management of Patients with Suspected or Confirmed Ovarian Cancer. | Yes | 2018-02-22 | 20 | 14 | 34 | 2015-11-08 | 2018-01-19 | 2015-11-24 | 2018-01-25 | 2018-02-08 | 2018-02-09 | I - Rare diseases | MROC HAS ANNUAL RECRUITMENT TARGET OF 6, APPROXIMATELY 10 IN TOTAL OVER THE LIFE OF THE TRIAL. | Neither
133814 | 16/SC/0439 | 199315 | The ACL SNNAP Trial: ACL Surgery Necessity in Non Acute Patients. | Yes | 2018-04-19 | 2 | 55 | 57 | 2017-11-02 | 2018-02-21 | 2017-10-25 | 2018-02-21 | 2018-02-23 | 2018-02-27 | I - Rare diseases | RECRUITMENT TARGET FOR THIS TRIAL IS APPROX 6 OVER THE LIFE OF THE TRIAL. | Neither
133815 | 18/SC/0015 | 236685 | Adjuvant canakinumab vs placebo in stages IB, II-IIIA resected NSCLC | No |  | 76 |  |  | 2018-04-17 | 2018-04-17 | 2018-02-23 | 2018-06-28 | 2018-07-02 | 2018-09-18 | H - Contracting delays | COMMERCIAL TRIALS FACILITATOR HAS BEEN BATTLING TO SECURE CONTRACTING ARRANGEMENTS WITH VARIOUS PARTIES INCLUDING SPONSOR | Neither
133816 | 17/LO/0731 | 219463 | PIVOTALboost: A phase III trial of prostate alone vs pelvic lymph node IMRT with or without prostate boost for intermediate and high risk localised prostate cancer | Yes | 2018-07-20 | 38 | 25 | 63 | 2018-03-22 | 2018-05-18 | 2017-07-27 | 2018-06-25 | 2018-06-25 | 2018-06-25 |  | PROJECT IS ON COURSE FOR RECRUITMENT TARGET. | Please Select...
133817 | 16/YH/0157 | 204585 | PLATO - PersonaLising Anal cancer radioTherapy dOse | No |  | 11 |  |  | 2017-08-02 | 2018-07-02 | 2016-07-20 | 2018-03-27 | 2018-07-13 | 2018-07-16 |  |  | Please Select...
133818 | 17/LO/0871 | 215297 | MePFAC | Yes | 2018-09-12 | 16 | 54 | 70 | 2018-05-03 | 2018-07-04 | 2018-04-17 | 2018-07-16 | 2018-07-20 | 2018-07-20 |  |  | Please Select...
133819 | 18/EM/0206 | 249915 | GS-UK-312-4639_RETRO-Idel | Yes | 2018-10-10 | 32 | 57 | 89 | 2018-05-16 | 2018-07-13 | 2018-07-12 | 2018-08-14 | 2018-08-14 | 2018-09-14 |  |  | Please Select...
133820 | 14/WS/1096 | 149204 | PARADIGM OlaPArib And RADiotherapy In newly-diagnosed GlioblastoMa: | Yes | 2018-09-27 | 10 | 62 | 72 | 2017-08-08 | 2018-07-17 | 2018-06-16 | 2018-07-02 | 2018-07-27 | 2018-08-07 |  |  | Please Select...
133821 | 17/LO/0334 | 214459 | FLO-ELA | Yes | 2018-10-31 | 33 | 34 | 67 | 2018-08-25 | 2018-08-25 | 2017-03-29 | 2018-09-27 | 2018-09-27 | 2018-10-16 |  |  | Please Select...
133822 | 18/EM/0091 | 242354 | NEFECON IN PATIENTS WITH PRIMARY IGA-Nephropathy Caliditas | No |  | 28 |  |  | 2017-11-30 | 2018-08-28 | 2018-06-14 | 2018-09-19 | 2018-09-25 | 2018-11-09 | I - Rare diseases | PROJECT HAS AN ANNUAL RECRUITMENT TARGET OF 1.4, EXPECTED TO BE A MAXIMUM OF 3 OVER THE LIFE OF THE PROJECT. | Neither
133823 | 17/SW/0190 | 227810 | Transmission of pneumococcus within family units (TOP study) | Yes | 2018-10-05 | 15 | 50 | 65 | 2008-08-01 | 2018-08-01 |  | 2018-08-16 | 2018-08-16 | 2018-09-28 |  |  | Please Select...
134075 | 16/EM/0344 | 180454 | MPP VARR | No |  | 9 |  |  | 2018-03-09 | 2018-10-02 | 2016-10-26 | 2018-10-11 | 2018-10-11 | 2018-10-11 |  | PLEASE NOTE, THE RECRUITMENT TARGET FOR MPP VARR IS 3 PATIENTS PER YEAR. | Please Select...
134079 | 18/LO/1311 | 248599 | GR40398 EFFICACY AND SAFETY OF RO6867461 IN DMO PATIENTS (RHINE) v1 | No |  | 29 |  |  | 2018-07-02 | 2018-10-03 | 2018-10-03 | 2018-10-30 | 2018-11-01 | 2018-11-05 |  |  | Please Select...
134087 | 17/YH/0120 | 208838 | DISC - Dupuytren's Interventions Surgery vs Collagenase | No |  | 0 |  |  | 2018-10-09 | 2018-11-05 | 2017-05-25 | 2018-11-05 | 2018-11-05 | 2018-11-15 |  |  | Please Select...
134089 | 18/LO/1522 | 249494 | OTO4811 | No |  | 0 |  |  | 2018-07-25 | 2018-11-08 | 2018-11-06 | 2018-11-08 | 2018-11-08 | 2018-12-04 |  | PLEASE NOTE THE RECRUITMENT TARGET FOR THIS PROJECT IS 2-3 PATIENTS PER YEAR. | Please Select...
134092 | 17/LO/1875 | 219487 | RAMPART - Renal Adjuvant MultiPle Arm Randomised Trial | No |  | 31 |  |  | 2018-08-03 | 2018-11-16 | 2018-01-08 | 2018-11-26 | 2018-12-17 | 2018-12-18 |  | PLEASE NOTE, THIS PROJECT HAS AN ANNUAL TARGET OF 4 PATIENTS PER YEAR. | Please Select...
134094 | 17/LO/1808 | 231108 | ICON 9 | No |  | 37 |  |  | 2018-08-03 | 2018-12-03 | 2017-12-18 | 2018-12-19 | 2019-01-09 |  |  | THIS PROJECT HAS A RECRUITMENT TARGET OF ZERO. | Please Select...