## Sheet1
GHNHSFT PERFORMANCE IN DELIVERING - QUARTER 3 - 2018/ 2019
Id | Research Ethics Committee Reference Number | Integrated Research Application System Number | Name of Trial | Target Number Of Patients Agreed? | Minimum Number Of Patients Agreed (Enter Same In Both If Only One Number) | Maximum Number Of Patients Agreed (Enter Same In Both If Only One Number) | Target Date To Recruit Patients Agreed? | Date Agreed to recruit target number of patients | Total Number Of Patients Recruited At The Agreed Target Date | Date That The Trial Closed To Recruitment | Total Number Of Study Participants Recruited | Reason For Closure Of Trial | Comments
35545 | 11/LO/0958 | 58575 | FAST FORWARD - To Identify A 5-Fraction Schedule Of Curative Radiotherapy Delivered In 1 Week That Is At Least As Effective And Safe As The Current UK Standard 15-Fraction Regimen Delivered Over 3 Weeks Following Primary Surgery For Early Breast Canc | Number Agreed | 5 | 77 | Date Agreed | 2018-08-31 | 77 | 2018-08-29 | 77 | Recruitment Finished | THIS PROJECT HAD AN ORIGINAL TARGET OF 5, THIS WAS BEFORE A SUBSTUDY WAS INCLUDED WITHIN THE PROJECT THAT THEN ENABLED FOR FURTHER RECRUITMENT AND IN TOTAL 77 WERE RECRUITED.
35546 | 17/WS/0088 | 224637 | A Two-Phase, Multicenter, Randomized Study Comparing Autologous Protein Solution with Hyaluronic Acid Intra Articular Injections in Patients with Knee Osteoarthritis | Number Agreed | 15 | 16 | Date Agreed | 2018-09-28 | 16 | 2018-09-13 | 16 | Recruitment Finished | PROJECT RECRUITED BEYOND ITS INTENDED RECRUITMENT TARGET.
35547 | 17/YH/0074 | 219173 | Studying Pleuroscopy in Routine Pleural Infection Treatment (SPIRIT) Trial | Number Agreed | 5 | 5 | Date Agreed | 2018-09-30 | 2 | 2018-09-30 | 2 | Recruitment Finished | PROJECT HAS RECRUITED TO TARGET.
35548 | 12/EE/0445 | 106714 | PREVENTT - A randomised double-blind controlled phase III study to compare the efficacy and safety of intravenous ferric carboxymaltose with placebo in patients with anaemia undergoing major open abdominal surgery | Number Agreed | 5 | 5 | Date Agreed | 2018-09-30 | 5 | 2018-09-30 | 5 | Recruitment Finished | PROJECT HAS BEEN RECRUITED TO TARGET.
35582 | 15/LO/0638 | 176799 | PAVE | Number Agreed | 15 | 24 | Date Agreed | 2018-10-02 | 24 | 2018-10-02 | 24 | Recruitment Finished | THIS PROJECT RECRUITED TO TIME AND TARGET, IT HAD A TARGET OF 15 AND RECRUITED 24. NO ISSUES WITH THIS PROJECT.