## Sheet1
Id | Research Ethics Committee Reference Number | Integrated Research Application System Number | Name of Trial | First Participant Recruited? | Date of First Participant Recruited | Duration between Date Site Selected and Date Site Confirmed | Duration between Date Site Confirmed and First Participant Recruited | Duration between Date Site Selected and First Participant Recruited | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Non-Confirmation Status | Date Site Ready To Start |  | Comments | Reasons for delay correspond to:
137597 | 18/SC/0015 | 236685 | Adjuvant canakinumab vs placebo in stages IB, II-IIIA resected NSCLC | No |  | 76 |  |  | 2018-04-17 | 2018-04-17 | 2018-02-23 | 2018-06-28 | 2018-07-02 | Please Select... | 2018-09-18 | H - Contracting delays | COMMERCIAL TRIALS FACILITATOR HAS BEEN BATTLING TO SECURE CONTRACTING ARRANGEMENTS WITH VARIOUS PARTIES INCLUDING SPONSOR | Neither
137598 | 17/LO/0731 | 219463 | PIVOTALboost: A phase III trial of prostate alone vs pelvic lymph node IMRT with or without prostate boost for intermediate and high risk localised prostate cancer | Yes | 2018-07-20 | 38 | 25 | 63 | 2018-03-22 | 2018-05-18 | 2017-07-27 | 2018-06-25 | 2018-06-25 | Please Select... | 2018-06-25 |  | PROJECT IS ON COURSE FOR RECRUITMENT TARGET. | Please Select...
137599 | 16/YH/0157 | 204585 | PLATO - PersonaLising Anal cancer radioTherapy dOse | No |  | 11 |  |  | 2017-08-02 | 2018-07-02 | 2016-07-20 | 2018-03-27 | 2018-07-13 | Please Select... | 2018-07-16 |  |  | Please Select...
137600 | 17/LO/0871 | 215297 | MePFAC | Yes | 2018-09-12 | 16 | 54 | 70 | 2018-05-03 | 2018-07-04 | 2018-04-17 | 2018-07-16 | 2018-07-20 | Please Select... | 2018-07-20 |  |  | Please Select...
137601 | 18/EM/0206 | 249915 | GS-UK-312-4639_RETRO-Idel | Yes | 2018-10-10 | 32 | 57 | 89 | 2018-05-16 | 2018-07-13 | 2018-07-12 | 2018-08-14 | 2018-08-14 | Please Select... | 2018-09-14 |  |  | Please Select...
137602 | 14/WS/1096 | 149204 | PARADIGM OlaPArib And RADiotherapy In newly-diagnosed GlioblastoMa: | Yes | 2018-09-27 | 10 | 62 | 72 | 2017-08-08 | 2018-07-17 | 2018-06-16 | 2018-07-02 | 2018-07-27 | Please Select... | 2018-08-07 |  |  | Please Select...
137603 | 17/LO/0334 | 214459 | FLO-ELA | Yes | 2018-10-31 | 33 | 34 | 67 | 2018-08-25 | 2018-08-25 | 2017-03-29 | 2018-09-27 | 2018-09-27 | Please Select... | 2018-10-16 |  |  | Please Select...
137604 | 18/EM/0091 | 242354 | NEFECON IN PATIENTS WITH PRIMARY IGA-Nephropathy Caliditas | No |  | 28 |  |  | 2017-11-30 | 2018-08-28 | 2018-06-14 | 2018-09-19 | 2018-09-25 | Please Select... | 2018-11-09 | I - Rare diseases | PROJECT HAS AN ANNUAL RECRUITMENT TARGET OF 1.4, EXPECTED TO BE A MAXIMUM OF 3 OVER THE LIFE OF THE PROJECT. | Neither
137605 | 17/SW/0190 | 227810 | TOP study -Transmission of pneumococcus within family units | Yes | 2018-10-05 | 15 | 50 | 65 | 2008-08-01 | 2018-08-01 | 2017-09-06 | 2018-08-16 | 2018-08-16 | Please Select... | 2018-09-28 |  |  | Please Select...
137606 | 16/EM/0344 | 180454 | MPP VARR | No |  | 9 |  |  | 2018-03-09 | 2018-10-02 | 2016-10-26 | 2018-10-11 | 2018-10-11 | Please Select... | 2018-10-11 | I - Rare diseases | PLEASE NOTE, THE RECRUITMENT TARGET FOR MPP VARR IS 3 PATIENTS PER YEAR. | Both
137607 | 18/LO/1311 | 248599 | RHINE GR40398 EFFICACY AND SAFETY OF RO6867461 IN DMO PATIENTS v1 | Yes | 2019-03-07 | 29 | 126 | 155 | 2018-07-02 | 2018-10-03 | 2018-10-03 | 2018-10-30 | 2018-11-01 | Please Select... | 2018-11-05 |  |  | Please Select...
137608 | 17/YH/0120 | 208838 | DISC - Dupuytren's Interventions Surgery vs Collagenase | Yes | 2019-02-05 | 0 | 92 | 92 | 2018-10-09 | 2018-11-05 | 2017-05-25 | 2018-11-05 | 2018-11-05 | Please Select... | 2018-11-15 |  |  | Please Select...
137609 | 18/LO/1522 | 249494 | OTO4811 | No |  | 0 |  |  | 2018-07-25 | 2018-11-08 | 2018-11-06 | 2018-11-08 | 2018-11-08 | Please Select... | 2018-12-04 |  | PLEASE NOTE THE RECRUITMENT TARGET FOR THIS PROJECT IS 2-3 PATIENTS PER YEAR. | Please Select...
137610 | 17/LO/1875 | 219487 | RAMPART - Renal Adjuvant MultiPle Arm Randomised Trial | No |  | 31 |  |  | 2018-08-03 | 2018-11-16 | 2018-01-08 | 2018-11-26 | 2018-12-17 | Please Select... | 2018-12-18 |  | PLEASE NOTE, THIS PROJECT HAS AN ANNUAL TARGET OF 4 PATIENTS PER YEAR. | Please Select...
137611 | 17/LO/1808 | 231108 | ICON 9 | No |  | 37 |  |  | 2018-08-03 | 2018-12-03 | 2017-12-18 | 2018-12-19 | 2019-01-09 | Please Select... |  |  | THIS PROJECT HAS A RECRUITMENT TARGET OF ZERO. | Please Select...
137616 | 17/EE/0213 | 201374 | Image guided radiotherapy and adaptive brachytherapy for cervix cancer | No |  | 15 |  |  | 2018-10-05 | 2019-01-21 | 2017-10-09 | 2019-01-29 | 2019-02-05 | Please Select... | 2019-02-11 |  |  | Please Select...
137617 | 18/SC/0222 | 223737 | NeoCLEAR | No |  |  |  |  | 2019-01-28 | 2019-01-28 | 2018-06-12 |  |  | Please Select... |  |  |  | Please Select...
137618 | 18/NW/0095 | 240776 | iMAP3 | No |  | 30 |  |  | 2019-02-08 | 2019-02-11 | 2018-04-12 |  | 2019-03-13 | Please Select... | 2019-03-18 |  |  | Please Select...
137619 | 18/EE/0272 | 242948 | CamPROBE | No |  | 38 |  |  | 2018-06-21 | 2019-02-19 | 2018-12-12 | 2019-03-06 | 2019-03-29 | Please Select... |  |  |  | Please Select...
137620 | 18/WA/0108 | 235402 | ICONS II: Identifying Continence OptioNs after Stroke | No |  |  |  |  | 2018-08-10 | 2019-02-22 | 2018-04-03 |  |  | Please Select... |  |  |  | Please Select...