## Sheet1
Id | Research Ethics Committee Reference Number | Integrated Research Application System Number | Name of Trial | First Participant Recruited? | Date of First Participant Recruited | Duration between Date Site Selected and Date Site Confirmed | Duration between Date Site Confirmed and First Participant Recruited | Duration between Date Site Selected and First Participant Recruited | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Non-Confirmation Status | Date Site Ready To Start | Reasons for Delay | Please use the free text comment box for more information about the trial. | Reasons for delay correspond to:
141907 | 16/YH/0157 | 204585 | PLATO - PersonaLising Anal cancer radioTherapy dOse | Yes | 2019-07-02 | 11 | 354 | 365 | 2017-08-02 | 2018-07-02 | 2016-07-20 | 2018-03-27 | 2018-07-13 | Please Select... | 2018-07-16 |  | This project has an anticipated annual recuitment of 1.9 participants per year | Please Select...
141908 | 17/LO/0871 | 215297 | MePFAC | Yes | 2018-09-12 | 16 | 54 | 70 | 2018-05-03 | 2018-07-04 | 2018-04-17 | 2018-07-16 | 2018-07-20 | Please Select... | 2018-07-20 |  |  | Please Select...
141909 | 18/EM/0206 | 249915 | GS-UK-312-4639_RETRO-Idel | Yes | 2018-10-10 | 32 | 57 | 89 | 2018-05-16 | 2018-07-13 | 2018-07-12 | 2018-08-14 | 2018-08-14 | Please Select... | 2018-09-14 |  |  | Please Select...
141910 | 14/WS/1096 | 149204 | PARADIGM OlaPArib And RADiotherapy In newly-diagnosed GlioblastoMa: | Yes | 2018-09-27 | 10 | 62 | 72 | 2017-08-08 | 2018-07-17 | 2018-06-16 | 2018-07-02 | 2018-07-27 | Please Select... | 2018-08-07 |  |  | Please Select...
141911 | 17/LO/0334 | 214459 | FLO-ELA | Yes | 2018-10-31 | 33 | 34 | 67 | 2018-08-25 | 2018-08-25 | 2017-03-29 | 2018-09-27 | 2018-09-27 | Please Select... | 2018-10-16 |  |  | Please Select...
141912 | 18/EM/0091 | 242354 | NEFECON IN PATIENTS WITH PRIMARY IGA-Nephropathy Caliditas | No |  | 28 |  |  | 2017-11-30 | 2018-08-28 | 2018-06-14 | 2018-09-19 | 2018-09-25 | Please Select... | 2018-11-09 | I - Rare diseases | PROJECT HAS AN ANNUAL RECRUITMENT TARGET OF 1.4, EXPECTED TO BE A MAXIMUM OF 3 OVER THE LIFE OF THE PROJECT. | Neither
141913 | 17/SW/0190 | 227810 | Transmission of pneumococcus within family units (TOP study) | Yes | 2018-10-05 | 15 | 50 | 65 | 2008-08-01 | 2018-08-01 | 2017-09-06 | 2018-08-16 | 2018-08-16 | Please Select... | 2018-09-28 |  |  | Please Select...
141914 | 16/EM/0344 | 180454 | MPP VARR | No |  | 9 |  |  | 2018-03-09 | 2018-10-02 | 2016-10-26 | 2018-10-11 | 2018-10-11 | Please Select... | 2018-10-11 | I - Rare diseases | This project has an anticipated annual recuitment of 3.5 participants per year | Both
141915 | 18/LO/1311 | 248599 | GR40398 EFFICACY AND SAFETY OF RO6867461 IN DMO PATIENTS (RHINE) v1 | Yes | 2019-03-07 | 29 | 126 | 155 | 2018-07-02 | 2018-10-03 | 2018-10-03 | 2018-10-30 | 2018-11-01 | Please Select... | 2018-11-05 |  |  | Please Select...
141916 | 17/YH/0120 | 208838 | DISC - Dupuytren's Interventions Surgery vs Collagenase | Yes | 2019-02-05 | 0 | 92 | 92 | 2018-10-09 | 2018-11-05 | 2017-05-25 | 2018-11-05 | 2018-11-05 | Please Select... | 2018-11-15 |  |  | Please Select...
141917 | 18/LO/1522 | 249494 | OTO4811 | Yes | 2019-05-13 | 0 | 186 | 186 | 2018-07-25 | 2018-11-08 | 2018-11-06 | 2018-11-08 | 2018-11-08 | Please Select... | 2018-12-04 |  | This project has an anticipated annual recuitment of 2.8 participants per year | Please Select...
141918 | 17/LO/1875 | 219487 | RAMPART - Renal Adjuvant MultiPle Arm Randomised Trial | Yes | 2019-05-25 | 31 | 159 | 190 | 2018-08-03 | 2018-11-16 | 2018-01-08 | 2018-11-26 | 2018-12-17 | Please Select... | 2018-12-18 |  | PLEASE NOTE, THIS PROJECT HAS AN ANNUAL TARGET OF 4 PATIENTS PER YEAR. | Please Select...
141919 | 17/LO/1808 | 231108 | ICON 9 | Yes | 2019-03-21 | 37 | 71 | 108 | 2018-08-03 | 2018-12-03 | 2017-12-18 | 2018-12-19 | 2019-01-09 | Please Select... | 2019-02-11 |  | This project has an anticipated annual recuitment of 5.2 participants per year | Please Select...
141920 | 17/EE/0213 | 201374 | Image guided radiotherapy and adaptive brachytherapy for cervix cancer | No |  | 15 |  |  | 2018-10-05 | 2019-01-21 | 2017-10-09 | 2019-01-29 | 2019-02-05 | Please Select... | 2019-02-11 |  | This project has an anticipated annual recuitment of 7.8 participants per year | Please Select...
141921 | 18/SC/0222 | 223737 | NeoCLEAR | No |  | 135 |  |  | 2019-01-28 | 2019-01-28 | 2018-06-12 | 2019-06-12 | 2019-06-12 | Please Select... | 2019-06-14 |  |  | Please Select...
141922 | 18/NW/0095 | 240776 | iMAP3 | Yes | 2019-04-02 | 30 | 20 | 50 | 2019-02-08 | 2019-02-11 | 2018-04-12 | 2019-03-13 | 2019-03-13 | Please Select... | 2019-03-18 |  |  | Please Select...
141923 | 18/EE/0272 | 242948 | CamPROBE | Yes | 2019-05-09 | 38 | 41 | 79 | 2018-06-21 | 2019-02-19 | 2018-12-12 | 2019-03-06 | 2019-03-29 | Please Select... | 2019-04-12 |  |  | Please Select...
141924 | 18/WA/0108 | 235402 | ICONS II: Identifying Continence OptioNs after Stroke | No |  | 68 |  |  | 2018-08-10 | 2019-02-22 | 2018-04-03 | 2019-04-24 | 2019-05-01 | Please Select... | 2019-05-16 |  |  | Please Select...
143266 | 17/SS/0082 | 222441 | SoSTART | Yes | 2019-06-20 | 35 | 43 | 78 | 2018-09-07 | 2019-04-03 | 2017-10-05 | 2019-04-26 | 2019-05-08 | Please Select... | 2019-05-29 |  | Planned recruitment target of 10 participants in 12 months | Please Select...
143267 | 19/EM/0047 | 257111 | GR40306 (TENAYA): A study of faricimab in nAMD | Yes | 2019-05-23 | 18 | 30 | 48 | 2018-11-28 | 2019-04-05 | 2019-04-04 | 2019-04-17 | 2019-04-23 | Please Select... | 2019-05-02 |  | Planned recruitment target of 4 participants in 12 months | Please Select...
143268 | 18/YH/0358 | 242342 | The Sunflower Study | Yes | 2019-06-20 | 38 | 34 | 72 | 2019-01-14 | 2019-04-09 | 2018-12-12 | 2019-04-09 | 2019-05-17 | Please Select... | 2019-05-30 |  |  | Please Select...
143277 | 18/NE/0296 | 248487 | CALIBRE Study | No |  |  |  |  | 2018-11-14 | 2019-04-15 |  |  |  | Please Select... |  |  |  | Please Select...
143278 | 19/SC/0148 | 41743 | XTEND Non-interventional Study | Yes | 2019-05-24 | 29 | 9 | 38 | 2019-04-01 | 2019-04-16 | 2019-05-10 | 2019-05-03 | 2019-05-15 | Please Select... | 2019-04-17 |  | Planned recruitment target of 6 participants in 12 months | Please Select...
143279 | 16/LO/1979 | 31860 | STATEC | No |  |  |  |  | 2018-02-28 | 2019-05-20 | 2016-12-20 | 2019-05-20 |  | Please Select... |  |  |  | Please Select...
143280 | 19/HRA/2404 | 41938 | The TIRED-UK Study | No |  | 0 |  |  | 2019-05-02 | 2019-05-23 | 2019-04-16 |  | 2019-05-23 | Please Select... |  |  |  | Please Select...
143281 | 19/NS/0046 | 40601 | SCP-EMEA-01 | No |  | 0 |  |  | 2019-05-02 | 2019-05-23 | 2019-04-16 |  | 2019-05-23 | Please Select... |  |  |  | Please Select...
143345 | 17/NI/0235 | 39959 | The MONARCH study | No |  | 67 |  |  | 2019-03-20 | 2019-04-25 | 2018-07-18 |  | 2019-07-01 | Please Select... |  |  |  | Please Select...