## PII Q2 2019
Id | Research Ethics Committee Reference Number | Integrated Research Application System Number | Name of Trial | First Participant Recruited? | Date of First Participant Recruited | Duration between Date Site Selected and Date Site Confirmed | Duration between Date Site Confirmed and First Participant Recruited | Duration between Date Site Selected and First Participant Recruited | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Non-Confirmation Status | Date Site Ready To Start | Reasons for delay | Comments | Reasons for delay correspond to:
148583 | 16/EM/0344 | 180454 | MPP VARR | Yes | 2019-08-28 | 9 | 321 | 330 | 2018-03-09 | 2018-10-02 | 2016-10-26 | 2018-10-11 | 2018-10-11 | Please Select... | 2018-10-11 | I - Rare diseases | This project has an anticipated annual recuitment of 3.5 participants per year | Neither
148584 | 18/LO/1311 | 248599 | GR40398 EFFICACY AND SAFETY OF RO6867461 IN DMO PATIENTS (RHINE) v1 | Yes | 2019-03-07 | 29 | 126 | 155 | 2018-07-02 | 2018-10-03 | 2018-10-03 | 2018-10-30 | 2018-11-01 | Please Select... | 2018-11-05 |  |  | Please Select...
148585 | 17/YH/0120 | 208838 | DISC - Dupuytren's Interventions Surgery vs Collagenase | Yes |  | 0 | 92 | 92 | 2018-10-09 | 2018-11-05 | 2017-05-25 | 2018-11-05 | 2018-11-05 | Please Select... | 2018-11-15 |  |  | Please Select...
148586 | 18/LO/1522 | 249494 | OTO4811 | Yes | 2019-05-13 | 0 | 186 | 186 | 2018-07-25 | 2018-11-08 | 2018-11-06 | 2018-11-08 | 2018-11-08 | Please Select... | 2018-12-04 | I - Rare diseases | This project has an anticipated annual recuitment of 2.8 participants per year | Neither
148587 | 17/LO/1875 | 219487 | RAMPART - Renal Adjuvant MultiPle Arm Randomised Trial | Yes | 2019-05-25 | 31 | 159 | 190 | 2018-08-03 | 2018-11-16 | 2018-01-08 | 2018-11-26 | 2018-12-17 | Please Select... | 2018-12-18 | I - Rare diseases | Please note this project has an annual target of 4 patients per year | Neither
148588 | 17/LO/1808 | 231108 | ICON 9 | Yes | 2019-03-21 | 37 | 71 | 108 | 2018-08-03 | 2018-12-03 | 2017-12-18 | 2018-12-19 | 2019-01-09 | Please Select... | 2019-02-11 | I - Rare diseases | This project has an anticipated annual recuitment of 5.2 participants per year | Neither
148589 | 17/EE/0213 | 201374 | Image guided radiotherapy and adaptive brachytherapy for cervix cancer | No |  | 15 |  |  | 2018-10-05 | 2019-01-21 | 2017-10-09 | 2019-01-29 | 2019-02-05 | Please Select... | 2019-02-11 | I - Rare diseases | This project has an anticipated annual recuitment of 7.8 participants per year | Neither
148590 | 18/SC/0222 | 223737 | NeoCLEAR | Yes | 2019-07-13 | 135 | 31 | 166 | 2019-01-28 | 2019-01-28 | 2018-06-12 | 2019-06-12 | 2019-06-12 | Please Select... | 2019-06-14 |  |  | Please Select...
148591 | 18/NW/0095 | 240776 | iMAP3 | Yes | 2019-04-02 | 30 | 20 | 50 | 2019-02-08 | 2019-02-11 | 2018-04-12 | 2019-03-13 | 2019-03-13 | Please Select... | 2019-03-18 |  |  | Please Select...
148592 | 18/EE/0272 | 242948 | CamPROBE | Yes | 2019-05-09 | 38 | 41 | 79 | 2018-06-21 | 2019-02-19 | 2018-12-12 | 2019-03-06 | 2019-03-29 | Please Select... | 2019-04-12 |  |  | Please Select...
148593 | 18/WA/0108 | 235402 | ICONS II: Identifying Continence OptioNs after Stroke | Yes | 2019-07-23 | 68 | 83 | 151 | 2018-08-10 | 2019-02-22 | 2018-04-03 | 2019-04-24 | 2019-05-01 | Please Select... | 2019-05-16 |  |  | Please Select...
148594 | 17/SS/0082 | 222441 | SoSTART | Yes | 2019-06-20 | 35 | 43 | 78 | 2018-09-07 | 2019-04-03 | 2017-10-05 | 2019-04-26 | 2019-05-08 | Please Select... | 2019-05-29 |  | Planned recruitment target of 10 participants in 12 months | Please Select...
148595 | 19/EM/0047 | 257111 | GR40306 (TENAYA): A study of faricimab in nAMD | Yes | 2019-05-23 | 18 | 30 | 48 | 2018-11-28 | 2019-04-05 | 2019-04-04 | 2019-04-17 | 2019-04-23 | Please Select... | 2019-05-02 | I - Rare diseases | Planned recruitment target of 4 participants in 12 months | Neither
148596 | 18/YH/0358 | 242342 | The Sunflower Study | Yes | 2019-06-20 | 38 | 34 | 72 | 2019-01-14 | 2019-04-09 | 2018-12-12 | 2019-04-09 | 2019-05-17 | Please Select... | 2019-05-30 |  |  | Please Select...
148597 | 18/NE/0296 | 248487 | CALIBRE Study | No |  | 50 |  |  | 2018-11-14 | 2019-04-15 | 2018-10-19 | 2019-05-03 | 2019-06-04 | Please Select... | 2019-09-20 |  |  | Please Select...
148598 | 19/SC/0148 | 41743 | XTEND Non-interventional Study | Yes | 2019-05-24 | 29 | 9 | 38 | 2019-04-01 | 2019-04-16 | 2019-05-10 | 2019-05-03 | 2019-05-15 | Please Select... | 2019-04-17 | I - Rare diseases | Planned recruitment target of 6 participants in 12 months | Neither
148599 | 16/LO/1979 | 31860 | STATEC | No |  |  |  |  | 2018-02-28 | 2019-05-20 | 2016-12-20 | 2019-05-20 |  | Please Select... |  | C - Closed by sponsor | Withdrawn by the sponsor | Sponsor
148600 | 19/HRA/2404 | 41938 | The TIRED-UK Study | Yes | 2019-06-06 | 0 | 14 | 14 | 2019-05-02 | 2019-05-23 | 2019-04-16 | 2019-05-23 | 2019-05-23 | Please Select... | 2019-06-03 |  | ED staff to be approached during June 2019 - complete questionaire if they have time in their shift | Please Select...
148601 | 19/NS/0046 | 40601 | SCP-EMEA-01 | Yes | 2019-08-08 | 5 | 38 | 43 | 2019-11-09 | 2019-06-26 | 2019-04-25 | 2019-06-21 | 2019-07-01 | Please Select... |  |  |  | Please Select...
148711 | 17/NW/0247 | 222303 | AURORA | No |  | 0 |  |  | 2018-12-04 | 2019-08-07 | 2017-08-30 | 2019-07-01 | 2019-08-07 | Please Select... | 2019-09-05 | I - Rare diseases | Recruitment anticipated to be 1.6 participants per year. Date site selected is after date confirmed by sponsor as the sponsor required the contract to be signed before the full pack was released | Neither
148712 | 19/LO/0040 | 253233 | Apremilast Phase4 Study on Quality of life in psoriasis manifestations | No |  | 36 |  |  | 2019-02-21 | 2019-07-31 | 2019-02-19 | 2019-08-28 | 2019-09-05 | Please Select... | 2019-09-06 |  |  | Please Select...
148714 | 16/EM/0322 | 202096 | Tenecteplase in Wake-up Ischaemic Stroke Trial (TWIST) | No |  | 10 |  |  | 2018-10-10 | 2019-07-25 | 2017-08-18 | 2019-07-29 | 2019-08-04 | Please Select... | 2019-09-18 | I - Rare diseases | Anticipated recruitment is 2 particpants over the life of the 6 month trial | Neither
148715 | 17/SC/0434 | 209815 | The ADAPT-Sepsis TrialBiomarker-guided duration of antibiotic treatment for sepsis | No |  | 69 |  |  | 2019-02-13 | 2019-07-25 | 2017-10-23 | 2019-09-27 | 2019-10-02 | Please Select... | 2019-10-04 |  |  | Please Select...
148716 | 19/WA/0016 | 256826 | MASH | Yes | 2019-08-07 | 0 | 1 | 1 | 2018-07-13 | 2019-08-06 | 2019-01-30 | 2019-08-06 | 2019-08-06 | Please Select... | 2019-08-06 |  |  | Please Select...
148717 | 19/LO/0350 | 251317 | BRAID | No |  | 27 |  |  | 2019-03-22 | 2019-09-04 | 2019-05-08 | 2019-09-17 | 2019-10-01 | Please Select... | 2019-10-03 |  |  | Please Select...
148718 | 18/YH/0223 | 243476 | Study to evaluate conjugate MenACYW vaccine in the UK infant schedule | No |  | 1 |  |  | 2019-07-08 | 2019-09-25 | 2019-07-09 | 2019-09-25 | 2019-09-26 | Please Select... | 2019-10-10 |  |  | Please Select..