## PID
Id | Research Ethics Committee Reference Number | Integrated Research Application System Number | Name of Trial | First Participant Recruited? | Date of First Participant Recruited | Duration between Date Site Selected and Date Site Confirmed | Duration between Date Site Confirmed and First Participant Recruited | Duration between Date Site Selected and First Participant Recruited | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Non-Confirmation Status | Date Site Ready To Start | Reasons for Delay | Comments | Reasons for
155479 | 17/EE/0213 | 201374 | Image guided radiotherapy and adaptive brachytherapy for cervix cancer | No |  | 15 |  |  | 2018-10-05 | 2019-01-21 | 2017-10-09 | 2019-01-29 | 2019-02-05 | Please Select... | 2019-02-11 | I - Rare diseases | This project has an anticipated annual recuitment of 7.8 participants per year | Neither
155480 | 18/SC/0222 | 223737 | NeoCLEAR | Yes | 2019-07-13 | 135 | 31 | 166 | 2019-01-28 | 2019-01-28 | 2018-06-12 | 2019-06-12 | 2019-06-12 | Please Select... | 2019-06-14 |  |  | Please Select...
155481 | 18/NW/0095 | 240776 | iMAP3 | Yes | 2019-04-02 | 30 | 20 | 50 | 2019-02-08 | 2019-02-11 | 2018-04-12 | 2019-03-13 | 2019-03-13 | Please Select... | 2019-03-18 |  |  | Please Select...
155482 | 18/EE/0272 | 242948 | CamPROBE | Yes | 2019-05-09 | 38 | 41 | 79 | 2018-06-21 | 2019-02-19 | 2018-12-12 | 2019-03-06 | 2019-03-29 | Please Select... | 2019-04-12 |  |  | Please Select...
155483 | 18/WA/0108 | 235402 | ICONS II: Identifying Continence OptioNs after Stroke | Yes | 2019-07-23 | 68 | 83 | 151 | 2018-08-10 | 2019-02-22 | 2018-04-03 | 2019-04-24 | 2019-05-01 | Please Select... | 2019-05-16 |  |  | Please Select...
155484 | 17/SS/0082 | 222441 | SoSTART | Yes | 2019-06-20 | 35 | 43 | 78 | 2018-09-07 | 2019-04-03 | 2017-10-05 | 2019-04-26 | 2019-05-08 | Please Select... | 2019-05-29 |  | Planned recruitment target of 10 participants in 12 months | Please Select...
155485 | 19/EM/0047 | 257111 | GR40306 (TENAYA): A study of faricimab in nAMD | Yes | 2019-05-23 | 18 | 30 | 48 | 2018-11-28 | 2019-04-05 | 2019-04-04 | 2019-04-17 | 2019-04-23 | Please Select... | 2019-05-02 | I - Rare diseases | Planned recruitment target of 4 participants in 12 months | Neither
155486 | 18/YH/0358 | 242342 | The Sunflower Study | Yes | 2019-06-20 | 38 | 34 | 72 | 2019-01-14 | 2019-04-09 | 2018-12-12 | 2019-04-09 | 2019-05-17 | Please Select... | 2019-05-30 |  |  | Please Select...
155487 | 18/NE/0296 | 248487 | CALIBRE Study | Yes | 2019-12-19 | 50 | 198 | 248 | 2018-11-14 | 2019-04-15 | 2018-10-19 | 2019-05-03 | 2019-06-04 | Please Select... | 2019-09-20 |  |  | Please Select...
155488 | 19/SC/0148 | 41743 | XTEND Non-interventional Study | Yes | 2019-05-24 | 29 | 9 | 38 | 2019-04-01 | 2019-04-16 | 2019-05-10 | 2019-05-03 | 2019-05-15 | Please Select... | 2019-04-17 | I - Rare diseases | Planned recruitment target of 6 participants in 12 months | Neither
155489 | 16/LO/1979 | 31860 | STATEC | No |  |  |  |  | 2018-02-28 | 2019-05-20 | 2016-12-20 | 2019-05-20 |  | Please Select... |  | C - Closed by sponsor | Withdrawn by the sponsor | Sponsor
155490 | 19/HRA/2404 | 41938 | The TIRED-UK Study | Yes | 2019-06-06 | 0 | 14 | 14 | 2019-05-02 | 2019-05-23 | 2019-04-16 | 2019-05-23 | 2019-05-23 | Please Select... | 2019-06-03 |  | ED staff to be approached during June 2019 - complete questionaire if they have time in their shift | Please Select...
155491 | 19/NS/0046 | 40601 | SCP-EMEA-01 | Yes | 2019-08-08 | 5 | 38 | 43 | 2019-11-09 | 2019-06-26 | 2019-04-25 | 2019-06-21 | 2019-07-01 | Please Select... |  |  |  | Please Select...
155492 | 17/NW/0247 | 222303 | AURORA | No |  | 0 |  |  | 2018-12-04 | 2019-08-07 | 2017-08-30 | 2019-07-01 | 2019-08-07 | Please Select... | 2019-09-05 | I - Rare diseases | Recruitment anticipated to be 1.6 participants per year. Date site selected is after date confirmed by sponsor as the sponsor required the contract to be signed before the full pack was released | Neither
155493 | 19/LO/0040 | 253233 | Apremilast Phase4 Study on Quality of life in psoriasis manifestations | Yes | 2019-10-24 | 36 | 49 | 85 | 2019-02-21 | 2019-07-31 | 2019-02-19 | 2019-08-28 | 2019-09-05 | Please Select... | 2019-09-06 |  |  | Please Select...
155494 | 16/EM/0322 | 202096 | Tenecteplase in Wake-up Ischaemic Stroke Trial (TWIST) | No |  | 10 |  |  | 2018-10-10 | 2019-07-25 | 2017-08-18 | 2019-07-29 | 2019-08-04 | Please Select... | 2019-09-18 | I - Rare diseases | Anticipated recruitment is 2 particpants over the life of the 6 month trial | Neither
155495 | 17/SC/0434 | 209815 | The ADAPT-Sepsis TrialBiomarker-guided duration of antibiotic treatment for sepsis | Yes | 2019-10-21 | 69 | 19 | 88 | 2019-02-13 | 2019-07-25 | 2017-10-23 | 2019-09-27 | 2019-10-02 | Please Select... | 2019-10-04 |  |  | Please Select...
155496 | 19/WA/0016 | 256826 | MASH | Yes | 2019-08-07 | 0 | 1 | 1 | 2018-07-13 | 2019-08-06 | 2019-01-30 | 2019-08-06 | 2019-08-06 | Please Select... | 2019-08-06 |  |  | Please Select...
155497 | 19/LO/0350 | 251317 | BRAID | Yes | 2019-11-13 | 27 | 43 | 70 | 2019-03-22 | 2019-09-04 | 2019-05-08 | 2019-09-17 | 2019-10-01 | Please Select... | 2019-10-03 |  |  | Please Select...
155498 | 18/YH/0223 | 243476 | Study to evaluate conjugate MenACYW vaccine in the UK infant schedule | Yes | 2019-12-04 | 1 | 69 | 70 | 2019-07-08 | 2019-09-25 | 2019-07-09 | 2019-09-25 | 2019-09-26 | Please Select... | 2019-10-10 |  |  | Please Select...
156640 | 19/SC/0311 | 262176 | ASEPTIC | No |  |  |  |  | 2019-10-01 | 2019-11-11 | 2019-08-07 | 2019-12-10 |  | Please Select... |  |  |  | Please Select...
156659 | 18/SS/0055 | 239109 | R4VaD | Yes | 2020-01-10 | 45 | 14 | 59 | 2019-02-11 | 2019-11-12 | 2018-09-06 | 2019-12-20 | 2019-12-27 | Please Select... | 2020-01-07 |  |  | Please Select...
156669 | 19/LO/1271 | 265680 | DAVE | No |  | 19 |  |  | 2019-07-09 | 2019-11-14 | 2019-08-15 | 2019-12-11 | 2019-12-03 | Please Select... | 2019-12-12 |  |  | Please Select...
156670 | 17/NI/0235 | 232253 | The MONARCH study | Yes | 2019-07-18 | 67 | 17 | 84 | 2019-03-20 | 2019-04-25 | 2018-07-18 | 2019-06-25 | 2019-07-01 | Please Select... | 2019-07-02 |  |  | Please Select...
156672 | 17/WM/0401 | 210716 | The CIPHER Study - phase B | No |  | 27 |  |  | 2019-07-16 | 2019-11-21 | 2017-11-08 | 2019-12-09 | 2019-12-18 | Please Select... | 2020-01-14
156674 | 17/NW/610 | 224135 | The UK Complex Aneurysm Study ( UK COMPASS) | No |  |  |  |  | 2019-10-17 | 2019-12-11 | 2017-12-18 |  |  | Please Select... |  |  |  | Please Select...

## PII
Id | Research Ethics Committee Reference Number | Integrated Research Application System Number | Name of Trial | Target Number Of Patients Agreed? | Minimum Number Of Patients Agreed (Enter Same In Both If Only One Number) | Maximum Number Of Patients Agreed (Enter Same In Both If Only One Number) | Target Date To Recruit Patients Agreed? | Date Agreed to recruit target number of patients | Total Number Of Patients Recruited At The Agreed Target Date | Date That The Trial Closed To Recruitment | Total Number Of Study Participants Recruited | Reason For Closure Of Trial | Comments
44094 | 18/LO/0256 | 235992 | The EASEMENT Study | Number Agreed | 10 | 10 | Date Agreed | 2019-02-28 | 24 | 2019-12-31 | 24 | Recruitment Finished | Completed to time and above target with the agreement of the Sponsor in February 2019. Sponsor then came back to site and asked it to reopen to recruitment, and recruit as many participants as possible up to 31/12/2019
44095 | 18/LO/1691 | 248968 | INCB-MA-CPCML-402 | Number Agreed | 3 | 3 | Date Agreed | 2019-06-28 | 3 | 2019-06-28 | 3 | Recruitment Finished | Completed to time and target (date the trial closed has been amended to agreee with the date on CPMS)
44096 | 17/NE/0149 | 224550 | ROVA-T Maintenance in SCLC (MERU) | Number Agreed | 2 | 2 | Date Agreed | 2019-07-15 | 2 | 2019-07-15 | 2 | Recruitment Finished | Completed to time and target
44097 | 15/LO/1066 | 149302 | CANC - 3263 ADONIS | Number Agreed | 8 | 12 | Date Agreed | 2019-04-30 | 12 | 2019-04-30 | 12 | Recruitment Finished | Completed to time and above target
44101 | 18/HY/0492 | 256149 | MARIA M5M6 | Number Agreed | 20 | 20 | Date Agreed | 2019-09-03 | 22 | 2019-09-03 | 22 | Recruitment Finished | Completed to time and above target by the agreement of the Sponsor
44102 | 19/EM/0047 | 257111 | GR40306 (TENAYA): A study of faricimab in nAMD | Number Agreed | 4 | 4 | Date Agreed | 2019-10-24 | 5 | 2019-10-24 | 5 | Recruitment Finished | Completed to time and above target with the agreement of the Sponsor